## Read Me
Migration Project Plan Template
How to use this file
• Use this plan to track your shopping cart migration from preparation through go-live.
• Start with a Demo Migration so your timeline is based on evidence, not assumptions.
• Keep tasks outcome-focused.
• Use Status to manage readiness and unblock dependencies quickly.
• Add links in Evidence Link to screenshots, review notes, or sign-off records.
Example
The Example tab shows a realistic sequence for a Demo Migration, full migration, validation, Recent Data Migration, and go-live.

## Project Plan
Workstream | Task ID | Task Name | In-charge | Dependencies | Start Date | End Date | Duration (days) | Status | Milestone | Evidence Link | Notes

## Example
Workstream | Task ID | Task Name | Owner | Dependencies | Start Date | End Date | Duration (days) | Status | Milestone | Evidence Link | Notes
Discovery | D-01 | Confirm source and target platforms, access, and constraints | Project Lead |  | 2026-01-10 | 2026-01-12 | 3 | Completed |  |  | Focus on data migration scope and risk.
Discovery | D-02 | Inventory integrations and data dependencies (apps, modules, custom fields) | Tech Lead | D-01 | 2026-01-12 | 2026-01-14 | 3 | In Progress
Proof | P-01 | Run Demo Migration on complex products and top categories | Next-Cart, Ops Lead | D-02 | 2026-01-15 | 2026-01-15 | 1 | Not Started |  |  | Use best sellers and highest variant complexity.
Review | R-01 | Review demo results and confirm mapping decisions | Project Lead | P-01 | 2026-01-16 | 2026-01-16 | 1 | Not Started | Demo Review Sign-off
Scope | S-01 | Confirm Entity Points and select service model (Standard, Managed, Custom) | Project Lead | R-01 | 2026-01-16 | 2026-01-17 | 2 | Not Started
Build | B-01 | Prepare target store environment for receiving full data | Tech Lead | S-01 | 2026-01-17 | 2026-01-20 | 4 | Not Started
Migration | M-01 | Run full migration | Next-Cart, Ops Lead | B-01 | 2026-01-21 | 2026-01-21 | 1 | Not Started | Full Migration Complete
QA | Q-01 | Validate products, variants, navigation, customers, and orders | QA Lead | M-01 | 2026-01-22 | 2026-01-26 | 5 | Not Started | QA Sign-off
SEO | SEO-01 | Finalize redirect plan for priority URLs | SEO Lead | M-01 | 2026-01-22 | 2026-01-24 | 3 | Not Started
Launch | L-01 | Run Recent Data Migration close to cutover | Ops Lead | Q-01 | 2026-01-27 | 2026-01-27 | 1 | Not Started | Final Sync Complete
Launch | L-02 | Go-live cutover and smoke test | Project Lead | L-01 | 2026-01-27 | 2026-01-27 | 1 | Not Started | Go-live
Monitor | MON-01 | Monitor first 72 hours and log issues | Ops Lead | L-02 | 2026-01-27 | 2026-01-30 | 4 | Not Started