## Read Me
Migration Risk Register Template
How to use this file
• Use this register to track risks from discovery through post-launch stabilization.
• Review risks using Likelihood and Impact (1 to 5).
• Write mitigations as actions with owners.
• Review the register after the Demo Migration and again before go-live.
Example
The Example tab includes common migration risks such as variant integrity issues, redirect gaps, and module or app dependency.

## Risk Register
Risk ID | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | In-charge | Mitigation Plan | Trigger / Early Signal | Status | Last Reviewed | Notes
R-01
R-02
R-03
R-04
R-05
R-06
R-07
R-08
R-09
R-10
R-11
R-12
R-13
R-14
R-15
R-16
R-17
R-18
R-19
R-20
R-21
R-22
R-23
R-24
R-25
R-26
R-27
R-28
R-29
R-30
R-31
R-32
R-33
R-34
R-35
R-36
R-37
R-38
R-39
R-40

## Example
Risk ID | Risk Description | Category | Likelihood (1-5) | Impact (1-5) | In-charge | Mitigation Plan | Trigger / Early Signal | Status | Last Reviewed | Notes
R-01 | Variant options do not map correctly, causing wrong purchasable combinations | Data Integrity | High | Very High | QA Lead | Demo sample includes highest variant complexity. Validate purchase behavior before full run. | Demo results show missing or mislabeled options | Open | 2026-01-09
R-02 | Priority old URLs are not covered by redirects after launch | SEO & Redirects | Medium | Very High | SEO Lead | Create priority URL list early. Map old to new destinations. Validate before cutover. | 404 spike on top landing pages | Monitoring | 2026-01-09
R-03 | Module or app stores critical data outside standard fields, causing missing meaning | Data Integrity | Medium | High | Tech Lead | Inventory modules and custom fields. If required, scope Custom Jobs based on demo evidence. | Demo shows missing custom attributes used in filters | Mitigating | 2026-01-09
R-04 | Operational settings cause checkout or email disruptions after go-live | Operations | Low | Very High | Ops Lead | Run a go-live smoke test including a full test order and notification checks. | Test order fails or emails not received | Closed | 2026-01-09
R-05 | Timeline slips because validation is compressed into final week | Timeline | Low | Medium | Project Lead | Validate early using demo, then validate high-risk segments first. | Many unresolved defects 48 hours before cutover | Accepted | 2026-01-09