## Read Me
RACI Template (Roles and Responsibilities for Shopping Cart Migration)
How to use this file
• List the major activities in your migration project, then assign R, A, C, and I for each activity.
• Keep one Accountable owner per activity whenever possible.
• Use role names, not individual names, then map roles to people separately.
• Review and update after your Demo Migration, when real complexity becomes visible.
Example
The Example tab includes typical roles such as Project Lead, Tech Lead, SEO Lead, QA Lead, and Next-Cart.

## RACI
Activity | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | Notes

## Example
Activity | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I) | Notes
Define migration scope and success criteria | Project Lead | Project Lead | Tech Lead, SEO Lead, Next-Cart | Project Lead
Run Demo Migration on representative sample | Next-Cart | Project Lead | Tech Lead | Project Lead | Include complex products and top categories.
Approve mapping decisions and service model | Project Lead | Sponsor | Tech Lead, Next-Cart | Project Lead, Tech Lead | Choose Standard vs Managed vs Custom based on demo evidence.
Execute full migration run | Next-Cart | Project Lead | Tech Lead | Project Lead
QA validation and sign-off | QA Lead | Project Lead | Tech Lead, SEO Lead, Next-Cart | Project Lead
Redirect coverage planning | SEO Lead | Project Lead | Next-Cart | Project Lead, SEO Lead | Focus on priority URLs first.
Recent Data Migration before go-live | Next-Cart | Project Lead | Tech Lead | Project Lead, Ops Lead | Schedule close to cutover.
Go-live cutover decision | Project Lead | Sponsor | Tech Lead, SEO Lead, Next-Cart | Project Lead
72-hour monitoring and incident triage | Ops Lead | Project Lead | Customer Support | Project Lead, Ops Lead